## Inspection Master Plan
Inspection Master Plan | [8 empty] | Code
Project Name |  |  |  |  | Project Version |  |  |  | CM Plan
Project Leader |  |  |  |  | Document Type |  |  |  | Feature List
Inspection Leader |  |  |  |  | Review Object |  |  |  | Feature Specification
Quality Officer |  |  |  |  | Doc Status |  |  |  | Functional Specification
Editor(s) |  |  |  |  | Total pages |  |  |  | HW Basic Design
Status | Entry Criteria |  |  |  | Exit Criteria |  |  | Status | HW Development Test Plan
| All source documents are in writing and have successfully exited with a known level of maximum remaining defects. Failing this, they will be mini-checked or sampled to determine their defect level before proceeding, and this will be noted on the document. Failing this, they will be clearly marked as NOT EXITED on all pages. |  |  |  | Check that the rate (pages or lines per hour) of individual checking did not exceed the known optimum rate by more than 40% on average. (Otherwise you may have missed too many defects which will then be sent on to others, even after correcting the defects you did find). |  |  |  | Integration Test Concept
| The applicable set of generic and specific rules for the task which produced the review object is available in writing. |  |  |  | Data summary is completed and sent to the database. |  |  |  | Planning Documents
| A formal master plan has been made for the rest of the checking task where the optimum recommended checking rate has been established and it is not faster than about 3 to 5 full pages per checking-hour if it is a document review, and it is not faster than about 100 to 150 NLOC per checking-hour if it is a code review. |  |  |  | For document review: There are no more than 0.25 major defects per page (or two to three for beginners!) remaining. For code review: There is no more than one major defect per 100 NLOC (or five for beginners!) remaining. |  |  |  | Project Plan
| The leader has been trained and is officially certified as an able practitioner. |  |  |  | All editing has been completed (i.e. you have successfully validated the edit in your follow-up). |  |  |  | Requirement Specification
| A cursory examination (<5 minutes) of a sample (page or so) of the review object shows less than one major per page findable. (Otherwise the author cleans up). |  |  |  | Either the author/owner or the Inspection leader can veto the exit based on their subjective belief that release would be a danger to their document customers. |  |  |  | SW Basic Design
| Ordinary text documentation shall have been cleaned up by a spelling checker before submission. Other possible machine checks or diagnostics have been done (clean compile, cross referencing, indexing, grammar check). | [7 empty] | SW Design
Documents | Name/Reference |  |  |  |  | Tag | Relevant sections | pages | SW Detailed Design
Review Object parts | [8 empty] | SW Development Test Plan
Checklists | [8 empty] | System Definition Profile
Sources | [8 empty] | System Design Specification (SPH)
Inspectors / checkers Name & Tel. |  |  | Additional Doc Role(s) |  | Pages/Lines | Special Assignments Role(s) / specific Checklists |  |  | System Integration Test Concept
System Integration Test Plan
System Test Specification Plan
System Test Specification Concept
User Documentation
User Documentation Concept
User Interface Basic Design
Meetings | Date | Location |  |  | Planned Start Time & End Time |  |  |  | User Interface Detailed Design
KickOff
Logging
Process B.
Planned Rates, Estimates
Your expected time for individual checking |  | Checking rates (pages/hour) |  |  |  | Expected average time to log an item (in meeting)
|  | Individual |  | Meeting
Mins | 0 | pages/hr |  | pages/hr |  | Mins
Note on A4: The inspection leader is the moderator of the inspection.
Note on A5: The Quality Officer of the project in which the review will be done. The Quality Officer has to be invited to every review meeting but it is not neccessary that the Quality Officer attends every meeting.
Note on A6: The Editor is the person who has written or programmed the documents to be inspected. He or she is the person who also has to fix the failures which have been found during the inspection.
Note on A14: Documents which are needed for the inspection
Note on A17: Additional files for understanding and using the program/document. (e.g. Automation.h, ReadMe.doc, ...)
Note on A18: The persons who participate in the inspection. (e.g. Checker 1 - n, Editor, Inspection leader)
Note on A28: Process Brainstorming
Note on B14: Name of the document or code that is to be examined. The exact filename must be used. (e.g. SPH.doc, Automation.cpp, ...)
Note on C25: The place at which the inspection meeting is being held. (e.g. NbgM, Room B323)
Note on C32: Is defined in the kickoff-meeting. Code inspection benchmark: The value has to be in a range of 100 to 150. Default statistic value is 100. Text inspection benchmark: The value has to be in a range of 3 to 5. Default statistic value is 3.
Note on D18: The Review Object parts which have to be inspected by the Inspector/Checker. Enter here the Document Reference Tags of the product parts which have to be inspected by the Inspector/Checker. (e.g. AUT, SPH, ...)
Note on E32: Is defined in the kickoff-meeting. Code inspection benchmark: The value depends on: Will a double check be executed in the session? If yes, then the default statistic value is 110. If no, then the default statistic value is 0. Text inspection benchmark: The value depends on: Will a double check be executed in the session? If yes, then the default statistic value is 4. If no, then the default statistic value is 0.
Note on F3: Select the appropriate type of the document (e.g. code, functional specification, software basic design,..) If the inspection is a code-review (e.g. C++, VB, C#, ...) then select code. If it is an inspection of documents (e.g. pdf, doc, ...) then select the appropriate text document. Depending on the selection of "code" or an "text document", certain phrases will change as well as the calculation of some formulas.
Note on F4: The review object which has to be inspected by the inspection team. (e.g. Object Frame class, SPH A&D Eng. Platform / Error Handling) The Review Object is handed in by the Editor.
Note on F5: Documents are assigned "preliminary" status while they are being created and their content is being coordinated. A document that an author has completed for review is assigned "baselined" status (thus, this status applies only to documents that will undergo a review). A document is assigned "released" status if it has been released.
Note on F6: Text inspection: The total number of pages in the whole document Code inspection: The total number of lines in the whole document
Note on F18: The pages or code lines which are to be checked by a person. (e.g. Page 513- 679, line 1200-1700)
Note on F25: The estimated time to accomplish an inspection meeting. (e.g. 10:00-16:00)
Note on G14: Document Reference Tags, Checklist Tags or Source Tags. Insert here the abbreviation of the file (e.g. AUT/SPH/...) This abbreviation is used in the Inspection Issue Log (Column: Document Reference Tag, Checklist Rule Tag). For entering more than one tag please use the Excel function ALT+ENTER.
Note on G18: Exactly specified tasks. (e.g. algorithm, guidelines, ...)
Note on G32: Is defined in the kickoff-meeting. Benchmark: Default statistic value is 2.
Note on H14: Relevant sections specifies which pages or code lines are essential. (e.g. Page 37 - 52, line 361 - 402, all, ...)
Note on I14: Text inspection: 1 page = 300 words Code inspection: Non-commentary lines of code (NLOC)

## Inspection Issue Log
Inspection Issue Log
No | Checker | Document Reference Tag | Doc. Page | Line No. | Type of item | New/ Duplicate | Checklist Rule Tag | Description If long explanation, remind: "say it in 7 words max!" | Number of occurance | comment | Editor note | Status
If necessary insert new lines only above this border
Major issues (with/without duplicates): |  |  |  |  | 0 | 0 | New issues found in meeting |  | 0
Minor issues (with/without duplicates): |  |  |  |  | 0 | 0 | Document Type |  | 0
Process Improvements (with/without duplicates): |  |  |  |  | 0 | 0 | Time spent for individual checking (mins)
Questions to the editor (with/without duplicates): |  |  |  |  | 0 | 0 | Review Object pages
Totals (with/without duplicates): |  |  |  |  | 0 | 0 | My check rate (Pages / Hrs spent)
Note on C1: Only one merge operation is allowed. For a new merge operation you have to restart the Excel-template. Using the Merge-Button you are able to select all review-templates which you want to merge together.
Note on C2: Refers to the Review object parts tag and the Source tag in the Master plan.
Note on E1: If it is a four eye review (author and checker) then you can push the Single-Merge Button for transfering the data to the Inspection Data Sum.
Note on F2: Major defect: Failure which could be very expensive if found too late Minor defect: The opposite of Major defect Process improvement (PI): An improvement suggestion to the software development process Question: A question to a specific part of the program or document
Note on F32: In this column the result is counted with duplicates
Note on G2: New: A new inspection comment is generated within the inspection meeting Duplicate: An existing inspection comment exists at least twice in the Inspection Issue log
Note on G32: In this column the result is counted without duplicates. Duplicates will be automatically subtracted from the Major, Minor, PI´s and Questions
Note on H2: Refers to the Checklist Tag in the Master plan
Note on I2: Please use this column during individual checking
Note on J2: If the same error occurs more than once, enter here the total number of occurance. If available enter in brackets the line numbers. Example: 4 (210, 300, 312)
Note on K2: Please use this column during the logging meeting
Note on L2: This column is used by the editor to document his decision about the issues.
Note on M2: CREATED: New request entered and assigned to Inspection Leader DEVELOPMENT: Request to be processed by Editor INTEGRATION: Bug fix or decision is ready for verification/test by Inspection Leader or other CLOSED: Bug fix verified by Inspection Leader or QE (to be stated via comment) DEFERRED: Deferred to later product versions REJECTED: Noted error turned out as no case of an error

## Inspection Data Sum
Inspection Data Summary
Phase |  |  |  |  | Document Type |  |  | 0
Date |  |  |  |  | Inspection Leader |  |  | 0
Review Object |  |  | 0 |  | Total pages |  |  | 0
Date Entry criteria passed |  |  |  |  | Date Exit criteria passed
Pre-checking time spend by Leader |  |  |  | Kickoff meeting |  |  |  | Total Pre-check time
Planning (min) |  | Entry Check (min) |  | No. People |  | Meeting (min) |  | 0
Individual Checking Results
Inspector Name | Pages studied |  | Time spent checking (min) |  | Major | Minor | PI | Question | Checking rate (p/h)
Time spent for Individual Checking |  |  | 0 |  | Average Checking rate (p/h)
Logging meeting
No. People |  | Meeting (min) |  | Pages double checked |  |  | Logging meeting rate (pages/h) |  | 0
Majors logged |  | Minors logged |  | PI Suggestions |  | Questions of intent |  | Total items logged
0 |  | 0 |  | 0 |  | 0 |  | 0
Average time to log an item (min) | [6 empty] | New items found in the meeting |  | 0
Time spent on issue detection (h) |  |  |  |  | 0
Final statistics from Editing, Followup and Exit
Major defects fixed |  | Minor defects fixed |  | CRs raised |  | PI Suggestions raised |  | Estimated time for find&fix a Major later (h)
|  | 0 |  | 0 |  | 0
Time spent by Editor (min) |  | Time spent by Leader in followup and exit (min) |  | Total time spent in this Inspection cycle (h) |  | Estimated time saved in this Inspection cycle (h) |  | Return on Investment
0
Achievable effectiveness (%) (estimated) |  | Real effectiveness (%) (estimated) |  | Estimated remaining Majors/page |  | Efficiency (Majors/h) |  | Cost time/Major (h/Major)
Note on A2: Requirements (P.M100-P.M150): The Review Object is defined during the Requirements phase. This phase includes activities to collect, evaluate, and package the requirements for the product to be developed. Analysis&Planning (P.M150-Q.P.M200): In the analysis section the properties (features) of the product/system are specified and a basic implementation concept (feature specification) is created. The first step is to identify the features of the Review Object. The features identified in this way are used for decisions pertaining to the overall architecture (Hardware, Software). Implementation (Q.P.M200-P.M260): The Review Object is constructed during the Implementation phase. The software developer writes the program code and performs the developer tests. System Test (P.M260-P.M270): The Review Object is system tested during the System Test phase. This primarily involves the overall function test, configuration test, and compatibility test.
Note on A4: The product which has to be inspected by the inspection team. (e.g. automation.cpp, SPH.doc, ...) The product is handed in by the editor.
Note on A5: If the Entry criteria in the Master Plan are fullfilled the date of the fulfillment will be shown.
Note on A6: Consists of Planning duration and Entry Check duration
Note on A18: Default: The number of people who handed in an inspection Exactly: The number of people who participated in the inspection meeting
Note on A19: Number of the Major defects (Duplicates are already subtracted)
Note on A24: All Major defects which are closed in the Inspection Issue Log will be shown here. Duplicates are already subtracted.
Note on A26: This is the time which the Editor has needed to fix all defects.
Note on A28: To estimate the value for the Achievable Effectiveness, choose the appropriate percentage for each of the following four criteria and add the four percentages together. 1. Actual number of review participants Choose 5% if fewer than planned Choose 15% if as planned 2. Level of participants ability and experience Choose 10% for basic level Choose 20% for advanced level Choose 30% for expert level 3. Structure and complexity of the review document Choose 5% for poorly structured documents and/or where the subject is highly complex Choose 10% for documents of average structure and complexity Choose 15% for clearly structured documents and/or where the subject is relatively simple 4. Document history Choose 10% if the document has been changed Choose 15% if the document is totally new
Note on B9: Text inspection: The number of pages studied Code inspection: The number of non-commentary lines of code (NLOC) studied
Note on C19: Number of the Minor defects (Duplicates are already subtracted)
Note on C24: All Minor defects which are closed in the Inspection Issue Log will be shown here. Duplicates are already subtracted.
Note on C28: = Achievable effectiveness (estimated) * Individual Checking rate / Average Checking rate"
Note on E6: Consists of Number of People and Meeting duration
Note on E18: Code review: The value depends if a double check was executed in the session. If yes, then number of NLOC double checked. Usually the same NLOC as documented in the master plan. If no, then the value is 0. Document review: The value depends if a double check was executed in the session. If yes, then number of pages double checked. Usually the same pages as documented in the master plan. If no, then the value is 0.
Note on E19: Number of the Process Improvement Suggestions (Duplicates are already subtracted)
Note on E24: Change Requests raised
Note on F2: Depending on the selection of "code" or other text documents in the cell document type in the Masterplan, certain phrases will change as well as the calculation of some formulas.
Note on F3: The inspection leader is the moderator of the inspection.
Note on F4: Text inspection: The total number of pages in the whole document Code inspection: The total number of lines in the whole document
Note on F5: If the Exit criteria in the Master Plan are fullfilled the date of the fulfillment will be shown.
Note on F9: Major defect: Failure which could be very expensive if found too late
Note on F16: Text inspection: Average checking rate in pages per hour (p/h) Code inspection: Average checking rate in non-commentary lines of code (NLOC) per hour
Note on G9: Minor defect: The opposite of Major defect
Note on G19: Number of the Questions of intent (Duplicates are already subtracted)
Note on G24: All Process Improvement Suggestions raised which are closed in the Inspection Issue Log will be shown here. Duplicates are already subtracted.
Note on G26: Approximately shows how much time have been saved by using this inspection. If the amount is negative then the inspection was unprofitable.
Note on H9: Process Improvement
Note on I6: The time which was spent before the checking phase.
Note on I9: Question or notes to the editor
Note on I19: Majors + Minors + PI + Questions
Note on I24: These are the estimated costs (h) that would arise if an error were found and fixed in a later phase. The earlier an error is found, the higher its cost-saving potential is. Please use the following default values for orientation in order to make your own estimation. Default statistic value for every defect not found is - if the review is done in the Requirements phase (P.M100-P.M150): 50 h. - if the review is done in the Analysis & Planning phase (P.M150-Q.P.M200): 30 h. - if the review is done in the Implementation phase (Q.P.M200-P.M260): 8 h. - if the review is done in the System Test phase (P.M260-P.M300): 2 h.
Note on I26: Hours saved by using this inspection. If the amount is negative then the inspection was unprofitable.
Note on J9: Text inspection: Is an indicator for how many pages have been studied per hour Code inspection: Is an indicator for how many non-commentary lines of code (NLOC) have been studied per hour